## Exception Inventory
RTMS Exception Inventory and Refactor Plan
Read-only audit of backend exception creation/handling and frontend error patterns. No source code was changed. Evidence is based on the current working tree scan.
Total findings | 22 | Critical | 2 | High | 11 | Medium | 9 | Low | 0 | 22
ID | Location | Layer | Exception / pattern | Current HTTP mapping | Message / contract issue | Severity | Refactor priority | Recommended target | Status | Evidence / notes
EX-001 | backend/src/main/java/com/rtms/backend/config/GlobalExceptionHandler.java:75-78 | Global error contract | RuntimeException catch-all | 404 RESOURCE_NOT_FOUND | All unchecked failures fall through to a not-found response; business conflicts and unexpected failures can be reported as 404 with raw exception text. | Critical | P0 | Replace with explicit domain exception hierarchy and a safe default 500 response; preserve a stable error envelope. | Open | Central blast radius. This is the first refactor checkpoint before changing individual services.
EX-002 | backend/src/main/java/com/rtms/backend/config/GlobalExceptionHandler.java:19-82 | Global error contract | Multiple exception-to-error-code mappings | Mixed: explicit handlers plus fallback | The API exposes several paths for status and error-code mapping; ResponseStatusException uses status heuristics and maps every 409 to INVALID_REVIEW_STATE. | High | P0 | Centralize mapping in one exception-to-problem-details policy with domain error codes owned by the domain layer. | Open | Affects client behavior even when HTTP status is correct.
EX-003 | backend/src/main/java/com/rtms/backend/config/ApiException.java:5-18; 40+ call sites | Application/domain boundary | ApiException carries HttpStatus | Explicit status from call site | Service and controller code must know transport-level HTTP status, coupling business logic to REST concerns. | High | P1 | Split domain exceptions from an adapter-level HTTP mapping; keep error code and safe message as domain data. | Open | Existing custom exception is useful as an inventory anchor but is transport-coupled.
EX-004 | backend/src/main/java/com/rtms/backend/service/*; controller/* | Exception taxonomy | RuntimeException for not-found resources | Usually 404 only because of catch-all | Many repositories use generic RuntimeException for missing horse, course, stall, task, report, plan, treatment or subject; semantics are implicit and inconsistent. | High | P0 | Introduce typed NotFound exceptions by aggregate/resource and replace generic orElseThrow lambdas incrementally. | Open | Representative examples: HorseService:132, StableStallService:49, GroomDailyTaskService:123, CourseService:42.
EX-005 | backend/src/main/java/com/rtms/backend/service/* | Exception taxonomy | IllegalArgumentException for validation and business rules | 400 VALIDATION_ERROR | Input validation, missing related resources, duplicate data and business constraints share the same exception type and often bypass structured field errors. | High | P1 | Use request validation for shape errors and typed domain exceptions for business rule violations; define a stable error-code catalog. | Open | Representative examples: AdmissionManagerReviewService:71, HorseTrainingPlanService:221-271, SubjectService:40-61.
EX-006 | backend/src/main/java/com/rtms/backend/service/* | Exception taxonomy | IllegalStateException for domain conflicts | Usually 500 or 404 through fallback | State conflicts such as occupied stall, duplicate review, locked horse, invalid admission state and cancelled workout are not represented as conflict/unprocessable semantics consistently. | Critical | P0 | Introduce Conflict/InvalidState domain exceptions mapped to 409 or 422 according to a documented matrix. | Open | Representative examples: HorseService:211, AdmissionManagerReviewService:55-162, HorseTrainingPlanService:248-545.
EX-007 | backend/src/main/java/com/rtms/backend/service/AdmissionGroomReviewService.java:63-194 | Admission workflow | ResponseStatusException in Groom review | Mostly explicit 400/404/409 | Groom admission logic is closer to an HTTP contract but keeps transport exceptions in the service and duplicates status/message decisions. | Medium | P1 | Move admission review outcomes to named domain errors and let one adapter map them to the existing workflow contract. | Open | Keep current API behavior during migration because Groom UI depends on these statuses.
EX-008 | backend/src/main/java/com/rtms/backend/service/AdmissionManagerReviewService.java:52-162; AdmissionTrainerReviewService.java:50-117 | Admission workflow | Mixed generic exceptions across review stages | Inconsistent | Manager and Trainer review paths use IllegalArgumentException, IllegalStateException and RuntimeException for equivalent workflow outcomes. | High | P0 | Create one admission-review exception vocabulary shared by Groom, Trainer, Vet and Manager stages. | Open | Important for cross-role consistency and idempotent review actions.
EX-009 | backend/src/main/java/com/rtms/backend/service/AdmissionReviewService.java:38-71 | Admission workflow | orElseThrow() without an explicit exception | Framework default / potentially inconsistent | Bare Optional.orElseThrow makes the error type and API response dependent on the global fallback instead of the admission contract. | High | P1 | Replace with explicit typed not-found or invariant exceptions and add controller contract tests. | Open | Direct evidence at lines 70-71.
EX-010 | backend/src/main/java/com/rtms/backend/security/CustomAccessDeniedHandler.java:17-25; CustomAuthEntryPoint.java:17-25; GlobalExceptionHandler.java:24-28 | Security error contract | Security errors have separate servlet and MVC handlers | 401/403 with similar envelopes | Unauthorized and forbidden responses are generated in multiple places; message text and logging policy can drift. | Medium | P1 | Define one error response factory and shared security error codes; keep servlet entry-point integration thin. | Open | Do not merge authentication and authorization semantics; only unify the response contract.
EX-011 | backend/src/main/java/com/rtms/backend/config/GlobalExceptionHandler.java:30-37, 40-44 | Validation | Validation handler returns only first error | 400 VALIDATION_ERROR | Multiple field violations are collapsed into a single message, limiting frontend correction and observability. | Medium | P1 | Return structured field errors while preserving the existing top-level code/message for compatibility. | Open | Also review MethodArgumentTypeMismatch and malformed JSON responses together.
EX-012 | backend/src/main/java/com/rtms/backend/config/GlobalExceptionHandler.java:69-73 | Persistence boundary | Database/persistence exceptions are normalized without correlation detail | 500 INTERNAL_ERROR | The client gets a safe message, but server-side diagnostics and constraint-specific classification are not visible in this handler. | High | P1 | Add correlation ID and structured server logging; classify known integrity conflicts separately from unknown database failures. | Open | No raw SQL is returned here, which is good; preserve that behavior.
EX-013 | backend/src/main/java/com/rtms/backend/service/AdmissionFileStorage.java:60-84 | File storage | IOException and RuntimeException catch/rethrow | 400/404/500 ResponseStatusException | Storage failures are converted to transport exceptions inside a service; cleanup also ignores IOException, making diagnosis and retry behavior unclear. | Medium | P2 | Introduce storage-specific exceptions, explicit cleanup logging and a stable error code for unavailable documents. | Open | Review external-hosted document branch separately from local file branch.
EX-014 | backend/src/main/java/com/rtms/backend/scheduler/GroomDailyTaskScheduler.java:35; TrainingPlanStatusScheduler.java:52 | Background jobs | catch (Exception) around scheduled work | No HTTP response | Scheduled job failures are swallowed/logged at a broad boundary; partial work and retry policy are not represented in an error contract. | High | P1 | Define job-level failure policy: transaction boundary, retry/backoff, alerting and idempotency key per job run. | Open | This is not an API exception but is part of the refactor surface.
EX-015 | backend/src/main/java/com/rtms/backend/interceptor/HttpAuditInterceptor.java:57; AuditLogService.java:56 | Observability | catch (Exception) in audit paths | Request continues / audit behavior depends on implementation | Audit failures can be hidden and may not carry request correlation, actor or endpoint context consistently. | Medium | P2 | Use a dedicated audit failure policy: never break business requests, but emit structured logs/metrics with correlation data. | Open | Keep audit isolation explicit and tested.
EX-016 | backend/src/main/java/com/rtms/backend/service/AuthService.java:142-156 | Authentication | RuntimeException wraps token hashing and user lookup | 500 or 404 via fallback | Infrastructure failure and missing user are represented with generic runtime exceptions; auth failures can be misclassified. | High | P1 | Separate authentication failure, missing principal and cryptographic infrastructure exceptions; never expose internal cause text. | Open | Review together with CustomAuthEntryPoint and refresh-token errors.
EX-017 | backend/src/main/java/com/rtms/backend/service/GroomIncidentReportService.java:40-195 | Groom incident workflow | RuntimeException/IllegalArgumentException/IllegalStateException mix | Inconsistent; some paths may become 404 | Incident validation, missing entities, state transitions and attachment errors use multiple generic types and include Vietnamese messages. | High | P1 | Define incident-report validation, not-found, conflict and attachment error codes; keep user-facing language at the API boundary. | Open | Relevant to the recent Groom incident-report UI issue.
EX-018 | backend/src/main/java/com/rtms/backend/service/HorseTrainingPlanService.java:221-848 | Training domain | Large service owns many generic business exceptions | Mixed 400/404/500 | Plan creation, assignment, scheduling, workout completion and capacity rules share one service and generic exception vocabulary. | High | P1 | Split by use case/domain policy first, then migrate exceptions to typed rule violations without changing behavior in one step. | Open | High change surface; refactor after the central error contract is defined.
EX-019 | backend/src/main/java/com/rtms/backend/service/RaceRegistrationService.java:55-192; PreventiveCareService.java:41-86; VetExamService.java:54-352 | Typed exception adoption | Some modules already use ApiException consistently | Mostly explicit | These services provide a useful migration reference, but error-code naming and 400 vs 409 choices still need a shared catalog. | Medium | P2 | Use these modules as compatibility baselines; standardize codes and response payload shape before broad migration. | Open | Positive existing pattern, recorded so refactor does not regress it.
EX-020 | frontend/src/services/api.ts:125; frontend/src/features/*/services/*.ts; frontend/src/features/*/components/* | Frontend error handling | Generic Error plus ad hoc catch UI | Client-specific | Frontend services throw generic Error/ApiError and components handle failures independently; message extraction and retry presentation can diverge. | Medium | P2 | Expose a typed client error model, centralized message mapping and shared loading/error/retry state components. | Open | Secondary scope: inventory only; no frontend changes were made.
EX-021 | backend/src/test/java/com/rtms/backend/service/*Test.java | Tests and contract | Tests assert generic exception classes | Test-level only | Tests lock in RuntimeException/IllegalStateException/IllegalArgumentException instead of the intended HTTP error contract for many paths. | Medium | P1 | Add controller/API contract tests first, then update service tests to assert typed domain errors and invariants. | Open | Representative tests: AdmissionManagerReviewServiceTest, HorseTrainingPlanServiceTest, GroomDailyTaskServiceTest.
EX-022 | backend/src/main/java/com/rtms/backend/**/*.java | Message consistency | Mixed English and Vietnamese exception messages | Message is returned in several handlers | Client-visible error messages are not language-neutral and may expose implementation/business details directly. | Medium | P2 | Use stable error codes plus localized client messages; keep server logs detailed and client payloads safe. | Open | Examples include HorseService, StableStallService, HorseTrainingPlanService and RaceRegistrationService.